## Sheet1
task | week | start date | end date | duration | project start date | project end date
1.1.1 Develop hardware and software plan | 2 | 2019-11-01 | 2019-11-15 | 14 | 2019-11-01 | 2020-10-30
1.1.2 Develop modelling plan | 4 | 2019-11-15 | 2019-12-13 | 28
1.1.3 Develop testing plan | 4 | 2019-12-13 | 2020-01-10 | 28
1.1.4 Integrate all plans | 2 | 2020-01-10 | 2020-01-24 | 14
1.2.1 Estimate workload | 1 | 2020-01-24 | 2020-01-31 | 7
1.2.2 Develop Positions and Payments for all roles | 3 | 2020-01-31 | 2020-02-21 | 21
1.3.1 Estimate risks | 4 | 2020-01-24 | 2020-02-21 | 28
1.3.2 Develop solutions for risks | 4 | 2020-02-21 | 2020-03-20 | 28
1.3.3 Develop monitoring scheme | 4 | 2020-03-20 | 2020-04-17 | 28
2.1 Recruit team members | 4 | 2020-01-24 | 2020-02-21 | 28
2.2 Assign roles and tasks for each of the members | 3 | 2020-02-21 | 2020-03-13 | 21
2.3 Mange the team | 2 | 2020-03-13 | 2020-03-27 | 14
3.1.1 Collect dataset of financial statement | 4 | 2020-03-27 | 2020-04-24 | 28
3.1.2 Collect other information in the form of text files | 6 | 2020-03-27 | 2020-05-08 | 42
3.2.1 Develop text-mining model | 4 | 2020-03-27 | 2020-04-24 | 28
3.2.2 Develop prediction model | 4 | 2020-03-27 | 2020-04-24 | 28
3.2.3 Integrate into text-mining model and prediction model into one final model | 3 | 2020-04-24 | 2020-05-15 | 21
3.3.1 Evaluate state of art algorithms | 3 | 2020-03-27 | 2020-04-17 | 21
3.3.2 Explore related python libraries | 3 | 2020-03-27 | 2020-04-17 | 21
3.3.3 Produce new algorithms that suited for the project | 3 | 2020-04-17 | 2020-05-08 | 21
3.4.1 Develop evaluation criteria | 2 | 2020-01-24 | 2020-02-07 | 14
3.4.2 Evaluate model under the criteria | 2 | 2020-05-15 | 2020-05-29 | 14
3.4.3 Optimize the model by the evaluation result | 4 | 2020-05-29 | 2020-06-26 | 28
4.1 Test the model on real-business case | 4 | 2020-06-26 | 2020-07-24 | 28
4.2 Gather test results | 2 | 2020-07-24 | 2020-08-07 | 14
4.3 Adjust the model according to test results | 4 | 2020-08-07 | 2020-09-04 | 28
5.1 Integrate model into business process | 4 | 2020-09-04 | 2020-10-02 | 28
5.2 Train staff for using the prototype | 4 | 2020-10-02 | 2020-10-30 | 28
6.1 Produce a maintenance schedule | 2 | 2020-10-02 | 2020-10-16 | 14
6.2 Produce an adaption plan | 2 | 2020-10-02 | 2020-10-16 | 14
Formulas:
start date = [project start date]
start date = [end date, row above]
end date = [start date]+[week]*7
project end date = MAX([end date]:D31)